## Earthquakes
Earthquakes Statement of Work
| Project Title |  | Start Date
| Register |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Chloe (Designer), DeAnna (Tester), Emilio (Lead), Taylor (SWE) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Chloe |  |  | 2025-11-22 | 2025-12-08 | 17 |  | Not Started
[7 empty] | Oh no, Assignment08's 700 points is a third of all points this semester and you have no commits! | In Progress
Complete
On Hold
Nov 26th: 0 commits
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| DeAnna |  |  | 2025-11-15 | 2025-12-08 | 24
| #10 Create Student class | Complete | SHA 21f9598, e081761 | 2025-11-15 | 2025-11-15 | 1
| #21 As an admin I want to be able to access student’s transcripts | Complete | SHA 109f87b , f573d19, 26d8a13, 3718357 | 2025-11-29 | 2025-11-29 | 1 | SHA 109f87b not a use case but necessary for code to run as intended
| #5 As a student I want to be able to see my previous schedules from other semesters | Complete | SHA 813d528, 0e43d79, c6466c3 | 2025-11-29 | 2025-11-29 | 1 | SHA c6466c3 is a test needed for pull request to be accepted
| #50 As a dev I want to be able to display the CRNs in descending order | Complete | SHA 2e5c0a5 , 1a6c1c6 | 2025-11-23 | 2025-11-23 | 1 | SHA 1a6c1c6 is a test needed for pull request to be accepted
| #34 As a designer I want the Admin menu to have Welcome message banner | Complete | SHA 42e5033 | 2025-11-23 | 2025-11-23 | 1
| #47 As a designer I want a label for that introduces the student before printing the student information | Complete | SHA 900e58e | 2025-11-23 | 2025-11-23 | 1
| #43 As a tester I want to test that the code runs following only the information given in the rule and requirements documentation | Complete |  | 2025-11-25 | 2025-11-25 | 1 | No SHA because it didn’t require code changes, just me runnning code
| #38 As a designer I want the student major to be displayed with ascii art | Complete | SHA 0ba8eb1 | 2025-11-23 | 2025-11-23 | 1
| #29 As a doc/writer I want a Attendance.csv | Complete | SHA 3a25d79 | 2025-11-23 | 2025-11-23 | 1 |  |  | Nov 26th: 31 commits, +1076, -281
| #22 As a tester I want to test the Course class | Complete | SHA 56d0e75 | 2025-11-25 | 2025-11-25 | 1
| #23 As a tester I want to test the Student class | Complete | SHA 376ae76, 6b80137 | 2025-11-25 | 2025-11-25 | 1 | SHA 6b80137 is fixing a design error I discovered during testing
| #20 As a dev I would like to be able to create a course to assign to a professor and/or students. | Complete | SHA cd4b81e, ed7e555 | 2025-11-25 | 2025-11-25 | 1 | SHA ed7e555 is a test needed for pull request to be accepted
| #40 As a designer I want the fiscal clearance label to be printed in all capital letters | Complete | SHA db6963e | 2025-11-25 | 2025-11-25 | 1
| # 16 As a dev I want a University Database.csv | Complete | SHA a4a5221 | 2025-11-15 | 2025-11-15 | 1
| #14 As a dev I want a Course class | Complete | SHA 4c3f236 , 2c0753d | 2025-11-17 | 2025-11-17 | 1
| #18 As a dev I want to be able to have a menu for the admin | Complete | SHA 91964cb | 2025-11-17 | 2025-11-17 | 1 | This SHA is for the user case to implement course class in admin_driver.py
| #24 Create unittests for Admin.py | Complete | SHA a3cf1fb | 2025-11-29 | 2025-11-29 | 1 | This user case was assigned to chloe, but the testing document was not made when I needed to create a test for my new Admin.py methods so I had to make the testing doc for Admin.py and decided to create tests the whole class, since I was already testing my methods.
| Upload standup_meetings.txt | Complete | SHA df55a75 | 2025-11-20 | 2025-11-20 | 1 | There is no user story number because this task was assigned during class
| Update tester name in README.md | Complete | SHA b82e2d7 | 2025-11-15 | 2025-11-15 | 1 | Task given by lead, not user story number
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Emilio |  |  | 2025-11-12 | 2025-12-08 | 27
| # Update README with 6 numbered, prioritized projects | On Hold | SHA 6b06d94, 08ed70b | 2025-11-12 | 2025-11-14 | 3 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 10 commits, +77, -30
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Taylor |  |  | 2025-11-22 | 2025-12-08 | 17
| #15 Create a Professor class |  | SHA 3f51e34, 8a2a698, b86d860, c3464c2, 825723b, ff508cc, 330ecc6, cd4b81e | 2025-11-23 | 2025-11-23 | 1
Nov 26th: 11 commits, +1505, -637
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL