## Earthquakes
Earthquakes Statement of Work
| Project Title |  | Start Date
| Register |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Chloe (Designer), DeAnna (Tester), Emilio (Lead), Taylor (SWE) |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments
| Chloe |  |  | 2025-11-22 | 2025-12-08 | 17
Oh no, Assignment08's 700 points is a third of all points this semester and you have no commits!
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| DeAnna |  |  | 2025-11-15 | 2025-12-08 | 24
| #10 Create Student class | Complete | SHA 21f9598, e081761 | 2025-11-15 | 2025-11-15 | 1
| #21 As an admin I want to be able to access student’s transcripts | Complete | SHA 109f87b , f573d19, 26d8a13, 3718357 | 2025-11-29 | 2025-11-29 | 1 | SHA 109f87b not a use case but necessary for code to run as intended
| #5 As a student I want to be able to see my previous schedules from other semesters | Complete | SHA 813d528, 0e43d79, c6466c3 | 2025-11-29 | 2025-11-29 | 1 | SHA c6466c3 is a test needed for pull request to be accepted
| #50 As a dev I want to be able to display the CRNs in descending order | Complete | SHA 2e5c0a5 , 1a6c1c6 | 2025-11-23 | 2025-11-23 | 1 | SHA 1a6c1c6 is a test needed for pull request to be accepted
| #34 As a designer I want the Admin menu to have Welcome message banner | Complete | SHA 42e5033 | 2025-11-23 | 2025-11-23 | 1
| #47 As a designer I want a label for that introduces the student before printing the student information | Complete | SHA 900e58e | 2025-11-23 | 2025-11-23 | 1
| #43 As a tester I want to test that the code runs following only the information given in the rule and requirements documentation | Complete |  | 2025-11-25 | 2025-11-25 | 1 | No SHA because it didn’t require code changes, just me runnning code
| #38 As a designer I want the student major to be displayed with ascii art | Complete | SHA 0ba8eb1 | 2025-11-23 | 2025-11-23 | 1
| #29 As a doc/writer I want a Attendance.csv | Complete | SHA 3a25d79 | 2025-11-23 | 2025-11-23 | 1
| #22 As a tester I want to test the Course class | Complete | SHA 56d0e75 | 2025-11-25 | 2025-11-25 | 1
| #23 As a tester I want to test the Student class | Complete | SHA 376ae76, 6b80137 | 2025-11-25 | 2025-11-25 | 1 | SHA 6b80137 is fixing a design error I discovered during testing
| #20 As a dev I would like to be able to create a course to assign to a professor and/or students. | Complete | SHA cd4b81e, ed7e555 | 2025-11-25 | 2025-11-25 | 1 | SHA ed7e555 is a test needed for pull request to be accepted
| #40 As a designer I want the fiscal clearance label to be printed in all capital letters | Complete | SHA db6963e | 2025-11-25 | 2025-11-25 | 1
| # 16 As a dev I want a University Database.csv | Complete | SHA a4a5221 | 2025-11-15 | 2025-11-15 | 1
| #14 As a dev I want a Course class | Complete | SHA 4c3f236 , 2c0753d | 2025-11-17 | 2025-11-17 | 1
| #18 As a dev I want to be able to have a menu for the admin | Complete | SHA 91964cb | 2025-11-17 | 2025-11-17 | 1 | This SHA is for the user case to implement course class in admin_driver.py
| #24 Create unittests for Admin.py | Complete | SHA a3cf1fb | 2025-11-29 | 2025-11-29 | 1 | This user case was assigned to chloe, but the testing document was not made when I needed to create a test for my new Admin.py methods so I had to make the testing doc for Admin.py and decided to create tests the whole class, since I was already testing my methods.
| Upload standup_meetings.txt | Complete | SHA df55a75 | 2025-11-20 | 2025-11-20 | 1 | There is no user story number because this task was assigned during class
| Update tester name in README.md | Complete | SHA b82e2d7 | 2025-11-15 | 2025-11-15 | 1 | Task given by lead, not user story number
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Emilio |  |  | 2025-11-12 | 2025-12-08 | 27
edit README | #62 Update README with 6 numbered, prioritized projects | Complete | SHA 6b06d94, 08ed70b | 2025-11-12 | 2025-11-14 | 3
| #9 As the team lead I want to make sure everyone knows how to issue a pull request | Complete | SHA 1bcf60f | 2025-11-14 | 2025-11-14 | 1
| #53 As a lead I want to have a meeting before the release #2 due date to make sure that at least half the tasks are finished | Complete |  | 2025-11-23 | 2025-11-23 | 1 | Via Zoom
| #48 As a Team lead i would like to make sure everyone is on track | Complete |  | 2025-11-12 | 2025-12-01 | 19 | Via Text/Zoom. Throughout the project I reached out on our preferred messaging system and aswell privilty
edit README | #57 As the lead I want an SDD doc | Complete | SHA f6ff4db | 2025-12-01 | 2025-12-01 | 1
clear_screen(), load_student(), and calls | Setting up file structure | Complete | SHA daa4a26 | 2025-11-15 | 2025-11-15 | 1
.gitignore, main_menu(), run_java_signup(), login() SignUp (main, studentSignUp, professorSignUp, adminSignUp, loadPin, generateID) | #7 As a student I want to be able to register for my XULA account. Entering Name, email, Password, etc. | Complete | SHA f75b0f3 | 2025-11-14 | 2025-11-15 | 2
update new README | #30 As a doc/writer I want a updated README about our Release #2 | Complete | SHA 788a70c | 2025-11-25 | 2025-11-25 | 1
Admin (__init__, display_info, add_to_database, open) admin_driver(), load_admin(), and calls | #18 As a dev I want to be able to have a menu for the admin | Complete | SHA e035d4d | 2025-11-17 | 2025-11-17 | 1
manage_fiscal_clearance() and calls | #26 As an advisor I want to be able to change fiscal clearance | Complete | SHA da2fa49 | 2025-11-21 | 2025-11-21 | 1
update new README | #35 As a doc/writer I want a updated README about our Release #1 | Complete | SHA 78b2e2e | 2025-11-21 | 2025-11-21 | 1
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Taylor |  |  | 2025-11-22 | 2025-12-08 | 17
Professor (__innit__, display_info, assign_course, remove_course, add_to_database) and calls load_professor() and calls assign_professor() | #15 Create a Professor class | Complete | SHA 3f51e34, 8a2a698, b86d860, c3464c2, 825723b, ff508cc, 330ecc6, cd4b81e | 2025-11-23 | 2025-11-23 | 1
| Partial #20 As a developer I would like to be able to create a course to assign to a professor. | Complete | 99c1c48 | 2025-12-01 | 2025-12-01 | 1
pytest | #25 As a tester, I want to test the Professor class. | Complete | SHA e7527c7, daf03c2 | 2025-11-23 | 2025-12-01 | 9
pytest | #27 Test create_schedule function. | Complete | 256504b | 2025-11-25 | 2025-11-15 | -9
create_schedule() and calls | #37 As an swe, I want to create a new schedule with at most 19 credits. | Complete | SHA 0a86799 | 2025-11-23 | 2025-11-24 | 2
Se Row 65 | #42 As a developer, I want to be able to edit the new schedule being given to students. | Complete | SHA 0a86799 | 2025-11-24 | 2025-11-24 | 1
See Row 65, edited admin_driver | Partial #48 As a dev I want to be able to have a menu for the admin. | Complete | 0a86799, a6118ad | 2025-11-24 | 2025-12-01 | 8
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL